## Project Schedule
PROJECT SCHEDULE
PROJECT NAME |  |  | PROJECT MANAGER
Data Fusion Pipeline |  |  | Rohith Kumar Senthil Kumar
PROJECT DELIVERABLE
The goal of this project is to develop a data integration pipeline to combine data frommultiple sources into a unified format
SCOPE STATEMENT
This project should be capable of handling both structured and unstructured data in various formats, including JSON, XML, and YAML. It should also support image processing and allow transformations based on the user’s requirements. Users should be able to define rules for the provided data and reuse these rules to process similar data. The system should clean and transform the data, converting it into a unified format based on the user’s choice. If time permits, the project should be made scalable to handle data from big data sources, including real-time Change Data Capture (CDC) events.
START DATE | END DATE | OVERALL PROGRESS
2025-09-06 | 2025-09-08 | 0%
TASK NAME | ASSIGNED TO | START DATE | END DATE | DURATION (in days) | STATUS | COMMENTS
Set Kickoff Meeting | Rohith Kumar Senthil Kumar | 2025-06-09 | 2025-06-09 | 1 | Complete
Agree on Objectives | Rohith Kumar Senthil Kumar | 2025-06-10 | 2025-06-10 | 1 | Complete
Detailed Requirements | Rohith Kumar Senthil Kumar | 2025-06-11 | 2025-06-12 | 2 | Complete
Final Planning and Analysis | Rohith Kumar Senthil Kumar | 2025-06-13 | 2025-06-15 | 3 | In Progress
Basic data ingestion | Rohith Kumar Senthil Kumar | 2025-06-16 | 2025-06-22 | 7 | Not Started
Add image processing capabilities | Rohith Kumar Senthil Kumar | 2025-06-23 | 2025-06-29 | 7 | Not Started
DB Development | Rohith Kumar Senthil Kumar | 2025-06-30 | 2025-07-03 | 7 | Not Started
Implement rule-based system | Rohith Kumar Senthil Kumar | 2025-07-04 | 2025-07-06 | 2 | Not Started
Implement unified format conversion | Rohith Kumar Senthil Kumar | 2025-07-07 | 2025-07-13 | 7
UI Client | Rohith Kumar Senthil Kumar | 2025-07-14 | 2025-07-20 | 7 | Not Started
Testing | Rohith Kumar Senthil Kumar | 2025-07-21 | 2025-07-27 | 7 | Not Started
Big data integration | Rohith Kumar Senthil Kumar | 2025-07-28 | 2025-08-09 | 13 | Not Started
STATUS
Complete
In Progress
Not Started