## Project Schedule
PROJECT SCHEDULE
PROJECT NAME |  |  | PROJECT MANAGER
Data Fusion Pipeline |  |  | Rohith Kumar Senthil Kumar
PROJECT DELIVERABLE
The goal of this project is to develop a data integration pipeline to combine data frommultiple sources into a unified format
SCOPE STATEMENT
Project scope encompasses data ingestion from external sources (Kaggle and GitHub repositories), real-time stream processing, rule-based data transformations, dataframe fusion capabilities, and flexible output destinations.
START DATE | END DATE | OVERALL PROGRESS
2025-09-06 | 2025-09-08 | 100%
TASK NAME | ASSIGNED TO | START DATE | END DATE | DURATION (in days) | STATUS | COMMENTS
Set Kickoff Meeting | Rohith Kumar Senthil Kumar | 2025-06-09 | 2025-06-09 | 1 | Complete
Agree on Objectives | Rohith Kumar Senthil Kumar | 2025-06-10 | 2025-06-10 | 1 | Complete
Detailed Requirements | Rohith Kumar Senthil Kumar | 2025-06-11 | 2025-06-12 | 2 | Complete
Final Planning and Analysis | Rohith Kumar Senthil Kumar | 2025-06-13 | 2025-06-15 | 3 | Complete
Environment Setup | Rohith Kumar Senthil Kumar | 2025-06-15 | 2025-06-16 | 1 | Complete
Basic data ingestion | Rohith Kumar Senthil Kumar | 2025-06-16 | 2025-06-22 | 7 | Complete
DB Development | Rohith Kumar Senthil Kumar | 2025-06-30 | 2025-07-01 | 2 | Complete
Implement rule-based system | Rohith Kumar Senthil Kumar | 2025-07-02 | 2025-07-08 | 7 | Complete
Implement unified format conversion | Rohith Kumar Senthil Kumar | 2025-07-08 | 2025-07-13 | 6 | Complete
UI Client | Rohith Kumar Senthil Kumar | 2025-07-14 | 2025-07-20 | 7 | Complete
Testing | Rohith Kumar Senthil Kumar | 2025-07-21 | 2025-07-27 | 7 | Complete
STATUS
Complete
In Progress
Not Started